## Sheet1
User story | # | Task | Responsible | Assignees | Estim. effort (h) | Priority (A-E) | Reason for priority
As a user, I want to be able to interact with the script via a web-based interface | 1 | Build interface for managing scripts | Floris | Floris | 4 | D | Script management. Not completely necessary as we can use mock data
| 2 | Design interface for managing scripts | Floris | Floris | 1 | D | Script management. Not completely necessary as we can use mock data
As a camera controller, I want to be able to see my running script during recording, along with actions, cameras and presets | 3 | Design interface for the camera controller | Joris | Joris, Floris | 1 | A | It is important to have a design before we implement the interface
| 4 | Implement the camera controller interface | Floris | Shane, Floris | 7 | B | If we have one interface completely functional we can integrate all other functionalities and other views/interfaces are then easier to make fully functional
| 5 | Implement front-end streaming implementation for push updates to the script data and running position | Hidde | Hidde, Joris | 4 | A | Time-based synchronization for running scripts
| 6 | Implement back-end streaming implementation for push updates to the running script data | Hidde | Hidde, Joris | 4 | B | Time-based synchronization for running scripts
| 7 | Create concurrency tests to test multiple users interacting with live system | Hidde | Hidde, Joris | 4 | B | Time-based synchronization for running scripts, quality assurance
As a user, I want to run a script to connect to the cameras represented in the database over IP commands | 8 | Create module in system to communicate with API of camera type | Shane | Shane | 4 | C | Base for all functionality with cameras
| 9 | Set up test environment for mocking camera's and/or connecting to a VPN provided by PolyCast | Shane | Shane | 3 | B | Base for all functionality with cameras
As a recording director, I want an interface to manage my script during recording, with director controls | 10 | Finish the User Interface of the director. This does not include advanced features. | Floris | Floris, Shane | 6 | A | Our app is all about UX/UI so we really want to have this done as early as possible
| 11 | Create concurrency tests to test controls overriding other and streaming connection | Joris | Joris, Hidde | 2 | B | Streaming is important for the interaction with the cameras
As a developer, I want a good environment to keep track of data | 12 | Create a SQL database | Shane | Shane | 2 | D | An SQL database could come in handy