## Main
User story | # | Task | Responsible | Assignees | Estim. effort (h) | Actual Effort | Done (yes/no) | Notes
As a user, I want to be able to interact with the script via a web-based interface | 1 | Set up front-end typescript system to interact with Scripting api | Hidde | Hidde, Joris | 4 | 8 | yes | Front-end typescript library. Also added basic test
| 2 | Build interface for managing scripts | Shane | Shane | 4 | 0 | no
| 3 | Design interface for managing scripts | Shane | Shane | 1 | 0 | no
As a camera controller, I want to be able to see my running script during recording, along with actions, cameras and presets | 4 | Design interface for a script running mode | Floris | Floris, Shane | 1 |  | yes
| 5 | Build interface for script running mode | Floris | Floris, Shane | 4 | 9 | almost | 2/3 of the views are done. Only the live stream view has to be made, this also comes with some livestream possibilities. This can also be done using some stubs (which we'll probably do first)
| 6 | Implement front-end streaming implementation for push updates to the script data and running position | Hidde | Hidde, Jordy, Joris | 4 | 0 | no | Not yet a priority because front-end wasn't in a finished state
| 7 | Implement back-end streaming implementation for push updates to the running script data | Hidde | Hidde, Joris, Jordy | 4 | 0 | no | Not yet a priority because front-end wasn't in a finished state
| 8 | Create concurrency tests to test multiple users interacting with live system | Hidde | Hidde, Joris, Jordy | 4 | 0 | no | Not yet a priority because front-end wasn't in a finished state
As a user, I want to use a script with actions, cameras and presets defined in a database | 9 | Set up database system, including testing tools for mocking a local database | Jordy | Jordy | 5 | 8 | yes (Shane + Hidde) | Taken over by Shane and Hidde as this was an important feature. Hidde set up the system and Shane continued
| 10 | Create tables / objects for cameras, actions and presets | Jordy | Jordy | 2 | 2 | yes (Shane + Hidde) | No object for camera yet.
| 11 | Create table for sequential actions (scripts) | Jordy | Jordy | 2 | 2 | yes(Shane)
| 12 | Create server-side API for scripts, actions, cameras and preset management | Jordy | Jordy | 3 | 4 | yes (Shane + Hidde) | Taken over by Shane and Hidde as this was an important feature. Hidde set up the system and Shane continued
| 13 | Create unit tests and integration tests for server-side API | Jordy | Jordy | 3 | 4 | yes (Shane + Hidde) | Taken over by Shane and Hidde as this was an important feature. Hidde set up the system and Shane continued
| 14 | Integrate Java static analysis tools in current system (Checkstyle, etc) to match choice of going with Java | Joris | Joris, Hidde | 2 | 4 | yes | SBT does not support PMD, so that has to be checked manually
As a user, I want to run a script to connect to the cameras represented in the database over IP commands | 15 | Create module in system to communicate with API of camera type | Shane | Shane | 4 | 2 | no | API still hard to figure out. Another team found an interface specification which will hopefully help us move forward.
| 16 | Set up test environment for mocking camera's and/or connecting to a VPN provided by PolyCast | Shane | Shane | 3 |  | no
As a recording director, I want an interface to manage my script during recording, with director controls | 17 | Build director script running interface | Joris | Joris, Hidde | 4
| 18 | Design director script running interface | Joris | Joris, Hidde | 1 | 4 | yes | Had a couple iterations on the design
| 19 | Create concurrency tests to test controls overriding other and streaming connection | Joris | Joris, Hidde | 2 |  | no | Not yet a priority because front-end wasn't in a finished state